## TRACKER
ORDER INFORMATION | [8 empty] | ① ACTIVE SO & FG CREATION |  | ② BOM CREATION |  | ③ SMV UPDATE |  | ④ PLANT EXT & CODE CHANGE |  | ⑤ CR RELEASE |  | ⑥ PO |  | REMARKS / NOTES
BUY ORDER NAME | RESPONSIBLE | BUY QTY | TOTAL SO | TOTAL FG | REF ACTIVE FG | DEADLINE | OVERALL STATUS | CURRENT STEP | DATE DONE | STATUS | DATE DONE | STATUS | DATE DONE | STATUS | DATE DONE | STATUS | DATE DONE | STATUS | DATE DONE | STATUS | REMARKS / NOTES
SE GYMSHARK – SS26 Soft Sculpt Re-buy – Shadowline |  | 7713 | 4 | 1 |  | 30.04.2026 | COMPLETE | ✅ ALL COMPLETE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE | SMV follow-up done. Plant change pending (follow-up done). Currently at Step 4.
SE GYMSHARK - AW26 - SOFT SCULPT MAR BUY-1 - Shadowline |  | 20997 | 74 | 10 | 7001473758 | 18.06.2026 | COMPLETE |  |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE
SE GYMSHARK - SS26 Shadow Buy - Asialine |  | 46704 | 28 | 7 | 7001445952 | 24.04.2026 | COMPLETE | → ④ PLANT EXT & CODE CHANGE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE | Steps 1–3 done. Plant code error FIXED – mailed to Kishori. At Step 4. REF FG: 7001445952.
LULU – Sleekline – 6FA – Add Qtys |  | 1709 | 9 | 4 | 7001452177 | 23.03.2026 | COMPLETE | → ④ PLANT EXT & CODE CHANGE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE | Active SO & FG DONE. BOM PROCESSING. Deadline: 23.03.2026.
LW3DOBS- SLK |  | 13935 | 3 | 1 | 7001479673 | 16.06.2026 | COMPLETE |  |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE
LULU -Seamless Orders - Sleekline - 6FA- later transfer |  | 31697 | 15 | 5 | 7001462606 | 20.05.2026 | COMPLETE |  |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ⏳ PENDING
SE GYMSHARK – SS26 Shadow DEC Buy – Contourline |  | 25561 | 24 | 7 | 7001443456 | 20.04.2026 | COMPLETE | ✅ ALL COMPLETE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE | 🎉 FULLY COMPLETE – PO DONE. REF FG: 7001443456.
LULU – Sleekline – 6SP – Add Qtys |  | 25651 | 16 | 5 | 7001452172 | 20.03.2026 | COMPLETE | → ⑤ CR RELEASE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE | Active SO & FG DONE. BOM next. Deadline: 20.03.2026.
SE GYMSHARK 6AW- GEO BUY MARCH-- SLK |  | 54228 | 110 | 18 | 7001474027 | 06.07.2026 | COMPLETE |  |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE
WI26-LULU ADD - SLK | LAKSHAN | 5942 | 12 | 4 | 7001488845 | 02.07.2026 | IN PROGRESS |  |  | ✅ DONE |  | IN PROGRESS
SE GYMSHARK - SS26 Soft Sculpt - B2C7T - Contourline |  | 19273 |  | 12 | 7001462962 | 11.05.2026 | COMPLETE |  |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE
LULU – Sleekline – FA26 – LW1GOWS – Transfer CNTL |  | 46068 | 40 | 12 | 7001449920 | 10.04.2026 | COMPLETE | → ② BOM CREATION |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE | Active SO & FG DONE. BOM PENDING – needs Dilshan's assist (4 fabrics). Deadline: 10.04.2026.
FALL 26 MAR LULU Chase-SLK |  | 7189 | 11 | 4 | 7001477483 | 02.06.2026 | COMPLETE | → ⑤ CR RELEASE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE
SE GYMSHARK – AW26 Shadow JAN Buy – Contourline |  | 23916 | 45 | 3 | 7001446070 | — | COMPLETE | → ② BOM CREATION |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE | Active SO & FG done (except 2 samples). BOM file received from Suraj. REF FG: 7001446070.
SE GYMSHARK – AW26 Distance IYKYK Buy – Sleekline |  | 8693 | 32 | 4 | 7001447155 | — | COMPLETE | → ④ PLANT EXT & CODE CHANGE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE | Steps 1–2 done. SMV UPDATE PENDING – follow-up done. REF FG: 7001447155.
SE GYMSHARK – M26 ONYX Buy – Transfer from ASL |  | 477 | 4 | 4 |  | — | COMPLETE | → ⑥ PO |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE | Steps 1–4 done. CR Release pending. PO pending. Urgent – fabric delay transfer from ASL.
SE GYMSHARK – AW26 Shadow JAN Buy – Contourline (Add-on) |  | 9588 | 29 | 3 | 7001453015 | — | COMPLETE | → ⑤ CR RELEASE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  |  | Active SO & FG DONE. BOM next.
SE GYMSHARK - AW26 - GEO BUY - Sleekline |  | 98069 | 239 | 24 | 7001453358 |  | COMPLETE |  |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE
LULU -Seamless Orders from H056 & H150 -FA26- Sleekline |  | 622466 | 728 | 214 | 7001425058 - H056 7001421659 - H150 |  | COMPLETE |  |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE
LULU -Seamless Orders from H150 -FA26- - Contourline |  | 135883 | 257 | 40 | 7001433766 |  | ❌ BLOCKED |  |  | ❌ BLOCKED |  | ❌ BLOCKED |  | ❌ BLOCKED |  | ❌ BLOCKED |  | ❌ BLOCKED |  | ❌ BLOCKED
WI26-Chase-SLK | LAKSHAN | 84194 | 38 | 9 | 7001488586 | 02.07.2026 | IN PROGRESS |  |  | ✅ DONE |  | IN PROGRESS
SE GYMSHARK - 6AW- GEO Range- A4B5F & A5A2D |  | 38532 | 111 | 14 | 7001466707 |  | COMPLETE | → ⑤ CR RELEASE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE
SE GYMSHARK -6AW - Soft Sculpt MAR buy 1- SLK | LAKSHAN | 75891 | 235 | 27 | 7001473550 | 06.07.2026 | IN PROGRESS |  |  | ✅ DONE |  | IN PROGRESS
AW26 DISTANCE-A4B5F - SLK |  | 1485 | 7 | 2 | 7001479510 |  | COMPLETE | → ⑤ CR RELEASE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE
A1B2A transfer ASL to SLK |  | 1715 | 2 | 2 | 7001479503 |  | COMPLETE |  |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE
A1B5B transfer from CNTR to SLK |  | 21025 | 34 | 6 | 7001479505 |  | COMPLETE | → ⑤ CR RELEASE |  | ✅ DONE |  | IN PROGRESS |  | ⏳ PENDING |  | ⏳ PENDING |  | ⏳ PENDING |  | ⏳ PENDING
LULU -Seamless Orders - Sleekline - WI26 buy Allocation |  | 477362 | 582 | 85 | 7001475267 | 18.07.2026 | IN PROGRESS |  |  | ✅ DONE |  | IN PROGRESS
SE GYMSHARK -AW26 - Shadow MAR buy - SLK |  | 36679 | 53 | 7 | x |  | ⏳ PENDING |  |  | ✅ DONE
SE GYMSHARK -6AW- Shadow buy - SLK |  | 8998 | 31 | 4 | 7001474020 |  | ⏳ PENDING |  |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE |  | ✅ DONE
AW26 SOFT SCULPT MARBUY - B6C3Y - CONTRL | LAKSHAN | 62359 | 161 | 20 | 7001480448 |  | ⏳ PENDING
AW26 SOFT SCULPT MARBUY - B7C2V - SLK | LAKSHAN | 15101 | 76 | 10 | 7001480453 |  | ⏳ PENDING
AW26 SOFTSCULPT MARBUY2&3-B6C4T- CONTRL | LAKSHAN | 62359 | 81 | 10 | 7001480448 |  | ⏳ PENDING
Shadowline -B6C4T | LAKSHAN | 37162 | 81 | 11 | 7001491130 |  | ⏳ PENDING |  |  | ✅ DONE
Gymshark TRNF to ASL from SLK |  | 451 | 3 | 2 | 7001480457 |  | ⏳ PENDING
AW26 Shadow MayBuy1-SLK |  | 22986 | 12 | 4 | 7001480455 |  | ⏳ PENDING
53358
35 |  | 2152058 |  | 4 | 0 |  | 18
⚙️ 6-STEP BUY COMPLETION PROCESS FLOW → Each column pair = DATE DONE + STATUS → Fill date when step is completed
| ① ACTIVE SO & FG CREATION | ② BOM CREATION | ③ SMV UPDATE | ④ PLANT EXT & CODE CHANGE | ⑤ CR RELEASE
OVERALL STATUS LEGEND
COMPLETE
IN PROGRESS
BLOCKED
NOT STARTED
OVERDUE
STEP STATUS LEGEND
✅ DONE
🔄 IN PROGRESS
⏳ PENDING
❌ BLOCKED
Note on A31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Thread Shade Pending for One Color
Note on F31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Only Two FG’s are pending - Still not received PCD’S

## DASHBOARD
TOTAL BUYS | TOTAL QTY | ✅ COMPLETE | 🔵 IN PROGRESS | ❌ BLOCKED
35 | 2152058 | 0 | 4 | 0
⚙️ ACTIVE ORDERS PER STEP
① ACTIVE SO & FG CREATION |  |  | 29 | orders active
② BOM CREATION |  |  | 22 | orders active
③ SMV UPDATE |  |  | 22 | orders active
④ PLANT EXT & CODE CHANGE |  |  | 22 | orders active
⑤ CR RELEASE |  |  | 22 | orders active
⑥ PO |  |  | 19 | orders active
📋 STATUS BREAKDOWN
COMPLETE |  |  | 18 | orders
IN PROGRESS |  |  | 4 | orders
BLOCKED |  |  | 0 | orders
NOT STARTED |  |  | 0 | orders
OVERDUE |  |  | 0 | orders
⛔ ITEMS NEEDING ATTENTION
BUY ORDER |  |  | AT STEP | STATUS
SE VUORI – VM1198 – Transfer to Contourline |  |  | ⛔ ① ACTIVE SO & FG | BLOCKED
→ Open 'TRACKER' sheet to update step dates and statuses

## REFERENCE (hidden)
GYMSHARK – PO / SO REFERENCE DATA (from original Sheet1)
SO / REF NO | TYPE | STYLE 1 | STYLE 2 | PO NUMBER | UNITS |  | SUPPLIER | COLOURWAY | MODE | QTY
1001617763 | 10 |  | AMITY | BB2J | Sea | 448
GYMSHARK | Bulk | B5B9N | B5B9N | 1001617764 | 10 |  | AMITY | NBZG | Sea | 117
GYMSHARK | Bulk | B4B7G | B4B7G | 1001617766 | 10 |  | AMITY | NBZG | Sea | 623
GYMSHARK | Bulk | B4B7G | B4B7G | 1001617767 | 10 |  | AMITY | NBZG | Sea | 410
GYMSHARK | Bulk | B4B7G | B4B7G | 1001617762 | 10 |  | AMITY | NBZG | Sea | 185
1001617763
Source: Original uploaded file – Sheet1. Retained as reference data only.